## Executive Overview
BUGBOUNTYTRACK - WORK BREAKDOWN STRUCTURE (WBS)
Final Year Project (FYP) Engineering Charter & Governance Baseline
Project Parameter | Engineering Specification
Project Identifier | PTUT - PRJ - 089
Project Title | BugBountyTrack: Private Bug Bounty & Vulnerability Disclosure Platform
Academic Sub-Field | 9. Cybersecurity, Privacy & LegalTech
Single Accountable Author | Taha Asadullah (Roll No: 24-ST-013)
Academic Institution | Punjab Tianjin University of Technology (PTUT), Lahore
Department | Department of Software Engineering Technology
Session / Batch / Section | Session 2024–2028 / Batch 24-SET-Fall / Section SET-B
Official Student Email | 24-st-013@students.ptut.edu.pk
Project Supervisor | Sir Umar Hayat
Client Platform | Modern Web (Next.js 14+ App Router, React 18+, TypeScript 5.x, Tailwind CSS, OpenPGP.js)
Backend & Persistence | Unified Next.js Serverless on Vercel + PostgreSQL 16 on Neon via Prisma ORM (RLS)
Planned Workload | 424 Total Hours (264h Academic Baseline + 160h Commercial Launch across 18 Weeks)
Release State | Commercial Baseline & Academic Evaluation Specification (Version 3.2.0)

## Module-Wise WBS
WBS Code | Req ID | Module / Area | Work Package Name | Deliverable Scope & Acceptance Criteria | Start–End Week | Est. Hours | Human Owner | Predecessor | Status
WP-1.1 | FR-1.1 | MOD-1: Foundation & Security | Monorepo Scaffolding & CI Pipeline | Next.js 14+ monorepo, ESLint, Prettier, and GitHub Actions CI workflow | W1–W2 | 8 | Taha Asadullah | — | [READY]
WP-1.2 | FR-8.2 | MOD-1: Foundation & Security | PostgreSQL Schema, Neon RLS & Hash-Chained Audit | Prisma relational schema, PostgreSQL RLS tenant context, and append-only audit ledger with SHA-256 prev_hash | W1–W2 | 12 | Taha Asadullah | WP-1.1 | [READY]
WP-1.3 | FR-8.1 | MOD-1: Foundation & Security | Early Markdown AST Sanitization Engine | `rehype-sanitize` pipeline neutralizing OWASP XSS cheat sheet attack vectors | W1–W2 | 10 | Taha Asadullah | WP-1.1 | [READY]
WP-1.4 | NFR-04 | MOD-1: Foundation & Security | Design Tokens & Accessible UI Base | Tailwind CSS tokens meeting WCAG 2.2 AA (24 × 24 px touch targets) | W1–W2 | 10 | Taha Asadullah | WP-1.1 | [READY]
WP-2.1 | FR-1.3 | MOD-2: Identity & Multi-Tenancy | Tenant Registration Wizard & Profiles | Organization creation, slug reservation, and public program profile | W3–W4 | 8 | Taha Asadullah | WP-1.4 | [PLANNED]
WP-2.2 | FR-1.3 | MOD-2: Identity & Multi-Tenancy | Email / Password Auth & Database-Backed Sessions | Bcrypt/Argon2 password hashing, database-persisted session tokens, and secure HTTP-only cookies | W3–W4 | 11 | Taha Asadullah | WP-2.1 | [PLANNED]
WP-2.3 | FR-1.2 | MOD-2: Identity & Multi-Tenancy | Server-Enforced RBAC Middleware | Access control enforcing Owner, Defender, Hunter, and ReadOnly roles | W3–W4 | 11 | Taha Asadullah | WP-2.2 | [PLANNED]
WP-2.4 | FR-8.3 | MOD-2: Identity & Multi-Tenancy | Shared Store Rate Limiter & Turnstile CAPTCHA | Shared store rate limiting (Postgres/Upstash) and Turnstile CAPTCHA (5 req/hr/IP) | W3–W4 | 10 | Taha Asadullah | WP-1.2 | [PLANNED]
WP-3.1 | FR-2.1 | MOD-3: Policy & Cryptography Base | RFC 9116 security.txt Endpoint & Download | Compliant RFC 9116 text policy preview and download route per tenant | W5–W6 | 8 | Taha Asadullah | WP-2.1 | [PLANNED]
WP-3.2 | FR-2.2 | MOD-3: Policy & Cryptography Base | In-Browser Cleartext PGP Signing UI | Browser workflow signing security.txt inline using private signing key | W5–W6 | 11 | Taha Asadullah | WP-3.1 | [PLANNED]
WP-3.3 | FR-2.5 | MOD-3: Policy & Cryptography Base | DNS TXT Challenge Ownership Verifier | Node.js DNS challenge record lookup verifying domain ownership | W5–W6 | 11 | Taha Asadullah | WP-3.1 | [PLANNED]
WP-3.4 | FR-3.1 | MOD-3: Policy & Cryptography Base | WebCrypto Keypair Generator & Argon2 S2K KeyStore | Ed25519 signing + X25519 encryption keys stored in IndexedDB protected by OpenPGP Argon2 S2K | W5–W6 | 10 | Taha Asadullah | WP-2.2 | [PLANNED]
WP-4.1 | FR-3.3 | MOD-4: Cryptographic Intake & CVSS | Multi-Recipient OpenPGP Payload Encrypt | In-browser payload encryption targeting Org defenders + Hunter key with neutral operational labels | W7–W8 | 11 | Taha Asadullah | WP-3.4 | [PLANNED]
WP-4.2 | FR-3.5 | MOD-4: Cryptographic Intake & CVSS | Direct-to-R2 Presigned Attachment Upload | Client-side encrypted streaming binary uploads (≤ 25 MB) directly to Cloudflare R2 via presigned URLs | W7–W8 | 7 | Taha Asadullah | WP-4.1 | [PLANNED]
WP-4.3 | FR-4.1 | MOD-4: Cryptographic Intake & CVSS | Pure TypeScript CVSS 3.1 & 45-Vector Test | 8 Base metric scoring engine asserting 100% parity across FIRST.org suite in CVSS_TEST_FIXTURES.md | W7–W8 | 11 | Taha Asadullah | WP-1.1 | [PLANNED]
WP-4.4 | FR-5.1 | MOD-4: Cryptographic Intake & CVSS | In-Browser Decrypt & Basic Triage State | Passphrase key unlocking, decrypted triage view, and basic state transitions (NEW->TRIAGING->ACCEPTED); Week 7 Live Working Prototype | W7–W8 | 11 | Taha Asadullah | WP-4.1 | [PLANNED]
WP-5.1 | FR-5.2 | MOD-5: Triage & Commit Verification | Dual-Lane Threading Interface | Confidential conversation thread and private reviewer-only internal notes | W9–W10 | 10 | Taha Asadullah | WP-4.4 | [PLANNED]
WP-5.2 | FR-5.3 | MOD-5: Triage & Commit Verification | Metadata Notifications & Duplicate Link | Resend email dispatching metadata only; reviewer-driven duplicate linking | W9–W10 | 9 | Taha Asadullah | WP-5.1 | [PLANNED]
WP-5.3 | FR-6.2 | MOD-5: Triage & Commit Verification | GitHub REST API Commit SHA & Branch Check | GitHub API v3 lookup validating commit existence and branch compare inclusion across public/private repos | W9–W10 | 10 | Taha Asadullah | WP-5.1 | [PLANNED]
WP-5.4 | FR-6.3 | MOD-5: Triage & Commit Verification | Infrastructure Config SHA-256 Hash Binder | Non-code remediation hash generator and deployment environment recording | W9–W10 | 9 | Taha Asadullah | WP-5.3 | [PLANNED]
WP-6.1 | FR-7.2 | MOD-6: Attested Retest & Defense | Attested Retest State Machine & Closure | Attested retest state machine (3 distinct fan-out terminal states), failed retest loopback to ACCEPTED, and ticket reopening | W11–W12 | 10 | Taha Asadullah | WP-5.3 | [PLANNED]
WP-6.2 | FR-8.4 | MOD-6: Attested Retest & Defense | Storage Quota Monitor & Enforcer | Quota enforcement (50 MB DB per tenant / 512 MB Neon, 2 GB R2 per tenant / 10 GB free tier; 90% warning, 100% rejection) | W11–W12 | 6 | Taha Asadullah | WP-1.2 | [PLANNED]
ACAD-01 | EV-01 | ACAD: Evaluation & Usability | Controlled Peer Usability Study | Controlled evaluation with 3–5 peers across OWASP Juice Shop targets | W11–W12 | 8 | Taha Asadullah | WP-6.1 | [PLANNED]
ACAD-02 | EV-02 | ACAD: Evaluation & Usability | Final Project Report & Live Demo Defense | Comprehensive academic report, presentation slides, and defense demo | W11–W12 | 14 | Taha Asadullah | ACAD-01 | [PLANNED]
WP-BUF-1 | GOV-01 | GOV: Contingency & Buffer | Project Buffer & Defense Contingency | Distributed buffer for unexpected debugging, security fixes & defense trials | W1–W12 | 28 | Taha Asadullah | WP-1.1 | [PLANNED]
WP-7.1 | FR-1.3 | MOD-7: Commercial Launch | Auth Hardening, TOTP MFA & Password Reset | TOTP MFA enrollment, password reset with immediate session revocation, encrypted totp_secret at rest | W13–W14 | 14 | Taha Asadullah | WP-2.2 | [ROADMAP]
WP-7.2 | FR-1.4 | MOD-7: Commercial Launch | Guided Onboarding & Offline Org Recovery Key | Step-by-step wizard: DNS verification, Offline Master Recovery Key generation, mandatory backup test challenge | W13–W14 | 12 | Taha Asadullah | WP-3.2 | [ROADMAP]
WP-7.3 | FR-1.6 | MOD-7: Commercial Launch | Account-Less Guest Submission, Recovery & Invitations | Ephemeral Curve25519 key generation in browser, secret tracking URL issuance with client URI fragment (#token=...&key=...), exportable Guest Recovery Package, multi-device restoration UI (/report/restore), and tokenized private program access enforcement | W13–W14 | 10 | Taha Asadullah | WP-4.1 | [ROADMAP]
WP-7.4 | FR-8.4 | MOD-7: Commercial Launch | Direct-to-R2 Presigned Upload & Orphan Cleanup | Presigned S3/R2 direct upload route (`/api/uploads/presign`), upload quota verification at issuance, and automated orphan cleanup | W13–W14 | 10 | Taha Asadullah | WP-4.2 | [ROADMAP]
WP-7.5 | FR-5.4 | MOD-7: Commercial Launch | SLA Countdown Engine & Slack Webhooks | Hourly scheduled SLA cron check, notification outbox worker, visual countdown alerts, and Slack-compatible webhook payloads | W15–W16 | 12 | Taha Asadullah | WP-5.2 | [ROADMAP]
WP-7.6 | FR-7.7 | MOD-7: Commercial Launch | Redacted Evidence Export Engine (PDF & JSON) | Sanitized PDF and JSON closure summary generation documenting timeline, commit SHA/branch, deployment env, and retest attestations | W15–W16 | 10 | Taha Asadullah | WP-6.1 | [ROADMAP]
WP-7.7 | FR-8.6 | MOD-7: Commercial Launch | Merchant of Record (Lemon Squeezy) Billing | Lemon Squeezy checkout integration (49/mo Team & Free Tier), webhook handler, subscription downgrade, direct bank payouts to Pakistan | W15–W16 | 14 | Taha Asadullah | WP-2.1 | [ROADMAP]
WP-7.8 | FR-2.1 | MOD-7: Commercial Launch | Landing Page, Public Docs & Legal Pack | Marketing landing page, public documentation, free RFC 9116 generator tool, Terms of Service, Privacy Policy, DPA, and subprocessor list | W15–W16 | 18 | Taha Asadullah | WP-3.1 | [ROADMAP]
WP-7.9 | FR-8.1 | MOD-7: Commercial Launch | Application Security Hardening & Pen-Test Pass | Strict CSP, Subresource Integrity (SRI), CSRF protection on cookies, login/MFA lockout, SSRF checks on GitHub URLs, and self pen-test | W17–W18 | 16 | Taha Asadullah | WP-1.3 | [ROADMAP]
WP-7.10 | NFR-01 | MOD-7: Commercial Launch | Observability (Sentry), Environments & Uptime | Sentry error tracking, staging and production database migrations in CI, and external uptime monitoring (BetterStack/UptimeRobot) | W17–W18 | 12 | Taha Asadullah | WP-1.1 | [ROADMAP]
WP-7.11 | FR-1.2 | MOD-7: Commercial Launch | SuperAdmin Abuse Management & Console | Administrative dashboard to inspect tenant counts, view platform error rates, handle abuse reports, and suspend abusive tenants | W13–W14 | 8 | Taha Asadullah | WP-2.3 | [ROADMAP]
WP-7.12 | FR-8.7 | MOD-7: Commercial Launch | Disaster Recovery & GDPR Hard Deletion | Automated daily PostgreSQL + R2 backup restore drill in sandbox, customer hard-deletion workflow, and incident response runbook | W17–W18 | 8 | Taha Asadullah | WP-1.2 | [ROADMAP]
WP-BUF-2 | GOV-02 | GOV: Contingency & Buffer | Commercial Pilot Support & Launch Buffer | Buffer for unexpected billing edge cases, webhook debugging, and production pilot customer support | W17–W18 | 16 | Taha Asadullah | WP-7.7 | [ROADMAP]
|  |  |  | TOTAL ESTIMATED ENGINEERING HOURS: |  | 424

## RACI Matrix
Module Code | Module Name | Human Accountable (Taha) | Supervisor (Sir Umar) | Faculty Panel (PTUT) | Internal AI Advisory Squad
MOD-1 | Foundation, RLS & Markdown Sanitization | A / R | C | I | Advised by Arthur (Arch) & Cyra (Sec)
MOD-2 | Multi-Tenancy, Auth & Server RBAC | A / R | C | I | Advised by Marcus (Forge) & Cyra (Sec)
MOD-3 | RFC 9116 Policy & Browser Keygen | A / R | C | I | Advised by Victoria (Req) & Cyra (Sec)
MOD-4 | Client Cryptography & CVSS 3.1 | A / R | C | I | Advised by Cyra (Sec) & Elena (QA)
MOD-5 | Confidential Triage & GitHub Validation | A / R | C | I | Advised by Marcus (Forge) & Julian (UX)
MOD-6 | Attested Retest & Quota Management | A / R | C | I | Advised by Elena (QA) & Garrison (SRE)
MOD-7 | Commercial Deployment, Billing & Hardening | A / R | C | I | Advised by Garrison (SRE) & Nadia (Release)
ACAD | Usability Study & FYP Defense | A / R | C | I | Advised by Alexander (Steward) & Victoria (Req)

## Sprint Milestones
Sprint ID | Academic Weeks | Target Work Packages | Key Engineering Deliverables | Prerequisite Gates & Evaluation | Planned Hours | Status
Sprint 1 | Weeks 1–2 | WP-1.1 to WP-1.4 + Buffer (4h) | Monorepo scaffolding, PostgreSQL RLS schema, AST sanitization, and UI tokens | Gate 0: Foundation Review | 44 | [READY]
Sprint 2 | Weeks 3–4 | WP-2.1 to WP-2.4 + Buffer (4h) | Tenant registration, DB-backed sessions, server RBAC, and shared store rate limiter | Gate 1: Identity & Multi-Tenancy | 44 | [PLANNED]
Sprint 3 | Weeks 5–6 | WP-3.1 to WP-3.4 + Buffer (4h) | RFC 9116 download, in-browser PGP cleartext signing, DNS TXT verifier, Ed25519 keypair generator | Gate 2: Policy & Keys | 44 | [PLANNED]
Sprint 4 | Weeks 7–8 | WP-4.1 to WP-4.4 + Buffer (4h) | Dual-recipient encryption, direct R2 presigned upload, pure TS CVSS 3.1 engine, in-browser decryption | Gate 3: Working Prototype Demonstration | 44 | [PLANNED]
Sprint 5 | Weeks 9–10 | WP-5.1 to WP-5.4 + Buffer (6h) | Dual-lane triage threads, metadata email alerts, GitHub commit & branch compare validation, config SHA binder | Gate 4: Remediation Evidence | 44 | [PLANNED]
Sprint 6 | Weeks 11–12 | WP-6.1, WP-6.2, ACAD-01, ACAD-02 + Defense Buffer (6h) | Attested retest state machine, storage quotas, Juice Shop usability study, final thesis & demo defense | Gate 5: Academic FYP Defense Certified | 44 | [PLANNED]
Sprint 7 | Weeks 13–14 | WP-7.1, WP-7.2, WP-7.3, WP-7.4, WP-7.11 | TOTP MFA, offline recovery key onboarding, account-less guest intake & recovery, direct R2 upload hardening, SuperAdmin | Gate 6: Commercial Core Intake | 54 | [ROADMAP]
Sprint 8 | Weeks 15–16 | WP-7.5, WP-7.6, WP-7.7, WP-7.8 | SLA countdown engine & Slack webhooks, redacted PDF export, Lemon Squeezy MoR billing, landing page & legal | Gate 7: Commercial Operations Ready | 54 | [ROADMAP]
Sprint 9 | Weeks 17–18 | WP-7.9, WP-7.10, WP-7.12, WP-BUF-2 | Security hardening & pen-test pass, Sentry observability, disaster recovery sandbox drill, launch buffer | Gate 8: Commercial Production Release | 52 | [ROADMAP]
|  |  |  | TOTAL PLANNED SPRINT HOURS: | 424

## Zero-Cost Financial Model
Infrastructure Layer | Platform Provider | Provisioned Cloud Tier | Resource Allocations & Quotas | Monthly Cost ($USD)
Application & API Gateway | Vercel Cloud | Hobby Developer Tier | Edge CDN, serverless functions, global SSL certificate | 0
Relational Database | Neon Serverless | PostgreSQL Free Tier | 512 MB storage, connection pooling via PgBouncer (50 MB / tenant demo) | 0
Encrypted File Storage | Cloudflare R2 | Free Tier Object Storage | 10 GB storage allowance, zero egress bandwidth fees (2 GB / tenant demo) | 0
Transactional Email | Resend API | Developer Free Tier | 3,000 minimal-metadata triage notifications / month | 0
CI/CD Build Automation | GitHub Actions | Standard Runner Free Tier | 2,000 automated build & test minutes / month | 0
|  |  | TOTAL DEMO INFRASTRUCTURE COST: | 0